## NaboSupport
Estimate in man hours
Topic	FrontEnd / React Native	End Date	BackEnd / Node (Nest.js)	End Date	Unit Test / FE & BE
Environment Setup	4	23/12/19	5	25/1219
Accounts - wp_users {Oauth}	4	24/12/19	8	27/1219
Accounts - wp_users {Oauth}	1	25/1219	6	28/1219
Address – Map	16	26/1219	4	29/1219
Supporters	3	27/12/19	3	30/1219
LocalEye	5	28/12/19	2	31/1219
Help	4	29/12/19	0
Invite using SMS / (Show all the apps)	3	30/12/19
Invite using eMail	3	31/12/19
Multilingual / Support	16	02/01/20
Technical documentation	4	02/01/20
	63		28		0
Total Hours (FE + BE) / Without Unit Testing	91

## TASK COMPLETION-DATE WISE
S.No	Topic	Type	Time	St Date	Ed Date
1	Environment Setup	FE + BE	4	30/12/19	30/12/19
2	Accounts - wp_users {Oauth}	FE + BE	10	31/12/19	02/01/20
3	Supporters	FE + BE	9	03/01/20	04/01/20
4	Address – Map	FE + BE	18	04/01/20	07/01/20
5	LocalEye	FE + BE	9	08/01/20	09/01/20
6	Help	FE + BE	9	09/01/20	10/01/20
7	Invite using SMS / (Show all the apps)	BE	6	11/01/20	11/01/20
8	Invite using eMail	BE	6	13/01/20	13/01/20
9	Multilingual / Support	FE + BE	16	14/01/20	16/01/20
10	Unit Test – Junit	FE + BE	20	17/01/20	20/01/20
11	Technical documentation	FE + BE	4	21/01/20	21/01/20