## Data
Timetracker Report: Times Explorer |  | Created
2019-11-11 23:01
Date | Start | End | Hours | Estimated Hours | Person | TFSID | Title | State | Work Item Type | ID
2019-09-03 15:00 | 43711.625 | 43711.7917 | 4 | 4 | Logesh | 6499 | Admin - CIA001 - Login - Authentication | Done | Task | c649bb59-aee9-e911-80fb-0cc47a092dc6
2019-09-04 15:05 | 43712.6285 | 43712.7951 | 4 | 4 | Logesh | 6501 | Admin - CIA002 - Login - Revoke Login access | Done | Task | 6867da0b-afe9-e911-80fb-0cc47a092dc6
2019-09-04 15:06 | 43712.6292 | 43712.7958 | 4 | 4 | Logesh | 6503 | Admin - CIA003 - Login - Login as Supervisor / Staff | Done | Task | 68567827-afe9-e911-80fb-0cc47a092dc6
2019-09-05 14:45 | 43713.6146 | 43713.7812 | 4 | 4 | Logesh | 6507 | Admin - CIA005 - User Management - User - View List | Done | Task | d2b04648-ace9-e911-80fb-0cc47a092dc6
2019-09-03 14:47 | 43711.616 | 43711.7826 | 4 | 4 | Logesh | 6509 | Admin - CIA015 - User Management - Admin User - Search | Done | Task | 9458c77f-ace9-e911-80fb-0cc47a092dc6
2019-09-06 14:57 | 43714.6229 | 43714.8729 | 6 | 6 | Logesh | 6523 | Admin - CIA006 -User Management - User - View user details | Done | Task | 9a22dedf-ade9-e911-80fb-0cc47a092dc6
2019-09-23 | 43731 | 43731.9583 | 23 |  | Logesh | 6528 | Existing APIs Bug Fixing & Thumbnail changes | New | Product Backlog Item | 7c23857a-a6ee-e911-80fb-0cc47a092dc6
2019-08-27 15:20 | 43704.6389 | 43704.8889 | 6 | 6 | Logesh | 6791 | Admin API -> CIA050 -> Project Setup -> Project Setup | Done | Task | 9be5d521-b1e9-e911-80fb-0cc47a092dc6
2019-09-06 15:01 | 43714.6257 | 43714.7924 | 4 | 4 | Logesh | 6792 | Admin API -> CIA009 -> User Management -> User - Delete | Done | Task | bb676778-aee9-e911-80fb-0cc47a092dc6
2019-09-10 14:56 | 43718.6222 | 43718.7889 | 4 | 4 | Logesh | 6793 | Admin API -> CIA010 -> User Management -> User - Search | Done | Task | 05085cbf-ade9-e911-80fb-0cc47a092dc6
2019-08-27 14:53 | 43704.6201 | 43704.7868 | 4 | 8 | Logesh | 6794 | Admin API -> CIA011 -> User Management -> Admin User - View List | Done | Task | 49969976-ade9-e911-80fb-0cc47a092dc6
2019-08-30 14:54 | 43707.6208 | 43707.7875 | 4 | 8 | Logesh | 6794 | Admin API -> CIA011 -> User Management -> Admin User - View List | Done | Task | a6fec483-ade9-e911-80fb-0cc47a092dc6
2019-08-30 15:23 | 43707.641 | 43707.891 | 6 | 6 | Logesh | 6795 | Admin API -> CIA012 -> User Management -> Admin User - View/Edit user details | Done | Task | 2d048e88-b1e9-e911-80fb-0cc47a092dc6
2019-09-10 14:52 | 43718.6194 | 43718.7861 | 4 | 8 | Logesh | 6796 | Admin API -> CIA013 -> User Management -> Admin User - Activate/Inactivate | Done | Task | 0e68352f-ade9-e911-80fb-0cc47a092dc6
2019-09-11 14:52 | 43719.6194 | 43719.7861 | 4 | 8 | Logesh | 6796 | Admin API -> CIA013 -> User Management -> Admin User - Activate/Inactivate | Done | Task | ad94063a-ade9-e911-80fb-0cc47a092dc6
2019-09-11 14:51 | 43719.6188 | 43719.7854 | 4 | 4 | Logesh | 6797 | Admin API -> CIA014 -> User Management -> Admin User - Delete | Done | Task | 8ae3800d-ade9-e911-80fb-0cc47a092dc6
2019-09-12 14:50 | 43720.6181 | 43720.7014 | 2 | 10 | Logesh | 6798 | Admin API -> CIA007 -> User Management -> User - Activate/Inactivate | Done | Task | 0f280fe2-ace9-e911-80fb-0cc47a092dc6
2019-09-13 14:50 | 43721.6181 | 43721.9514 | 8 | 10 | Logesh | 6798 | Admin API -> CIA007 -> User Management -> User - Activate/Inactivate | Done | Task | 6bc8d2e8-ace9-e911-80fb-0cc47a092dc6
2019-09-05 | 43713 | 43713.0833 | 2 | 12 | Logesh | 6799 | API -> Existing Sprint Bug Fixing | In Progress | Task | fec44fe4-0ef1-e911-80fb-0cc47a092dc6
2019-09-09 | 43717 | 43717.25 | 6 | 12 | Logesh | 6799 | API -> Existing Sprint Bug Fixing | In Progress | Task | b1fb71ce-0ef1-e911-80fb-0cc47a092dc6
2019-09-09 00:40 | 43717.0278 | 43717.1111 | 2 | 12 | Logesh | 6799 | API -> Existing Sprint Bug Fixing | In Progress | Task | b6e27b8f-c8ea-e911-80fb-0cc47a092dc6
2019-10-03 15:42 | 43741.6542 | 43741.8208 | 4 | 12 | Logesh | 6799 | API -> Existing Sprint Bug Fixing | In Progress | Task | 02cb3f5b-c6e5-e911-80fb-0cc47a092dc6
2019-09-12 16:06 | 43720.6708 | 43720.8375 | 4 | 4 | Logesh | 6939 | Admin API - CIA008- User Management - Promote to admin | Done | Task | a149f289-b7e9-e911-80fb-0cc47a092dc6
2019-09-16 10:10 | 43724.4236 | 43724.7569 | 8 | 8 | Logesh | 7233 | API -> CIA016 -> Notification System -> Reports - View List | Done | Task | 96c3f4ad-16d9-e911-80fa-0cc47a092dc6
2019-09-17 15:34 | 43725.6486 | 43725.8153 | 4 | 4 | Logesh | 7234 | API -> CIA017 -> Notification System -> Reports - View Report details | Done | Task | a9651912-b3e9-e911-80fb-0cc47a092dc6
2019-09-17 15:35 | 43725.6493 | 43725.816 | 4 | 4 | Logesh | 7235 | API -> CIA018 -> Notification System -> Reports - Delete | Done | Task | 85025823-b3e9-e911-80fb-0cc47a092dc6
2019-09-18 21:52 | 43726.9111 | 43727.0778 | 4 | 4 | Logesh | 7236 | API -> CIA019 -> Notification System -> Reports - Search | Done | Task | 42959976-30da-e911-80fb-0cc47a092dc6
2019-09-19 12:17 | 43727.5118 | 43727.5951 | 2 | 2 | Logesh | 7237 | API -> CIA043 -> Notification System -> Reports - Pending Action | Done | Task | 241a785a-a9da-e911-80fb-0cc47a092dc6
2019-09-18 | 43726 | 43726.0833 | 2 | 1 | Logesh | 7238 | API -> CIA044 -> Notification System -> Reports - Block Account | Done | Task | 37c2db8a-9af0-e911-80fb-0cc47a092dc6
2019-09-18 | 43726 | 43726.0417 | 1 | 1 | Logesh | 7239 | API -> CIA020 -> Notification System -> Reports - Not a Violation | Done | Task | e4c2cc96-9af0-e911-80fb-0cc47a092dc6
2019-09-19 12:16 | 43727.5111 | 43727.5528 | 1 | 1 | Logesh | 7239 | API -> CIA020 -> Notification System -> Reports - Not a Violation | Done | Task | 4c77673c-a9da-e911-80fb-0cc47a092dc6
2019-09-19 21:39 | 43727.9021 | 43728.1521 | 6 | 6 | Logesh | 7240 | API -> CIA031 -> Points Setup -> View List | Done | Task | 1a50f5dd-f7da-e911-80fb-0cc47a092dc6
2019-09-20 10:58 | 43728.4569 | 43728.5403 | 2 | 8 | Logesh | 7241 | API -> CIA032 -> Points Setup -> Dollar definiition | Done | Task | 85943892-67db-e911-80fb-0cc47a092dc6
2019-09-20 18:06 | 43728.7542 | 43729.0042 | 6 | 8 | Logesh | 7241 | API -> CIA032 -> Points Setup -> Dollar definiition | Done | Task | e65b6b52-a3db-e911-80fb-0cc47a092dc6
2019-09-23 19:31 | 43731.8132 | 43732.1465 | 8 | 8 | Logesh | 7242 | API -> CIA033 -> Points Setup -> Package - Add | Done | Task | 483b53af-0ade-e911-80fb-0cc47a092dc6
2019-09-23 19:55 | 43731.8299 | 43731.9132 | 2 | 6 | Logesh | 7243 | API -> CIA034 -> Points Setup -> Package - Edit | Done | Task | 27301114-0ede-e911-80fb-0cc47a092dc6
2019-09-24 15:38 | 43732.6514 | 43732.8181 | 4 | 6 | Logesh | 7243 | API -> CIA034 -> Points Setup -> Package - Edit | Done | Task | d446a6a8-b3e9-e911-80fb-0cc47a092dc6
2019-09-25 20:40 | 43733.8611 | 43734.1111 | 6 | 6 | Logesh | 7244 | API -> CIA035 -> Points Setup -> Package - Delete | Done | Task | aa999fa0-a6df-e911-80fb-0cc47a092dc6
2019-09-26 14:59 | 43734.6243 | 43734.9576 | 8 | 8 | Logesh | 7751 | Admin - CIA021 - Notification System - Opportunities - View List | Done | Task | f8a8df30-aee9-e911-80fb-0cc47a092dc6
2019-09-27 15:40 | 43735.6528 | 43735.8194 | 4 | 4 | Logesh | 7753 | Admin - CIA022 - Notification System - Opportunities - View opportunity details | Done | Task | a22515f3-b3e9-e911-80fb-0cc47a092dc6
2019-09-27 15:41 | 43735.6535 | 43735.8201 | 4 | 4 | Logesh | 7755 | Admin - CIA023 - Notification System - Opportunities - Delete | Done | Task | 4e628510-b4e9-e911-80fb-0cc47a092dc6
2019-10-11 17:20 | 43749.7222 | 43749.8056 | 2 |  | Logesh | 8202 | CIA001> Login Validation is not working | QA Verified | Bug | ffedddd6-78ee-e911-80fb-0cc47a092dc6
2019-09-28 02:43 | 43736.1132 | 43736.1549 | 1 |  | Logesh | 8205 | CIA005 > Recent created user is not listing at top. | QA Verified | Bug | 793f4eaa-6be1-e911-80fb-0cc47a092dc6
2019-09-28 02:42 | 43736.1125 | 43736.1542 | 1 |  | Logesh | 8209 | CIA007 > User Message and Validation is not implemented as mentioned in FRD | QA Verified | Bug | 3e75af70-6be1-e911-80fb-0cc47a092dc6
2019-09-26 18:08 | 43734.7556 | 43734.7972 | 1 |  | Logesh | 8212 | CIA007 > Unable to reactivate the user, as inactive user is not listed out in Grid. | QA Verified | Bug | cc6b7b96-5ae0-e911-80fb-0cc47a092dc6
2019-09-28 02:44 | 43736.1139 | 43736.1556 | 1 |  | Logesh | 8218 | CIA005 > Admin privileged user is getting displayed in User tab which is wrong,. | QA Verified | Bug | 5be5bcb9-6be1-e911-80fb-0cc47a092dc6
2019-09-28 02:42 | 43736.1125 | 43736.1542 | 1 |  | Logesh | 8239 | CIA013> When inactivate user got activated again, no mail is triggered at that time. | QA Verified | Bug | 7a977679-6be1-e911-80fb-0cc47a092dc6
2019-10-10 | 43748 | 43748.0417 | 1 |  | Logesh | 8239 | CIA013> When inactivate user got activated again, no mail is triggered at that time. | QA Verified | Bug | 298c536b-96f0-e911-80fb-0cc47a092dc6
2019-10-11 17:27 | 43749.7271 | 43749.7688 | 1 |  | Logesh | 8239 | CIA013> When inactivate user got activated again, no mail is triggered at that time. | QA Verified | Bug | b1097dd4-79ee-e911-80fb-0cc47a092dc6
2019-09-28 02:44 | 43736.1139 | 43736.1556 | 1 |  | Logesh | 8240 | CIA014> Deleted account is not getting removed from Admin User Tab. | QA Verified | Bug | df0d5ecb-6be1-e911-80fb-0cc47a092dc6
2019-09-30 15:43 | 43738.6549 | 43738.8215 | 4 | 4 | Logesh | 8345 | API -> CIA024 -> Notification System -> Opportunities - Search | Done | Task | b75cde5b-b4e9-e911-80fb-0cc47a092dc6
2019-09-30 15:44 | 43738.6556 | 43738.7389 | 2 | 2 | Logesh | 8346 | API -> CIA047 -> Notification System -> Opportunities - Pending Action | Done | Task | d0b5366f-b4e9-e911-80fb-0cc47a092dc6
2019-09-30 15:44 | 43738.6556 | 43738.6972 | 1 | 1 | Logesh | 8347 | API -> CIA025 -> Notification System -> Opportunities - Block Account | Done | Task | c3030681-b4e9-e911-80fb-0cc47a092dc6
2019-09-30 15:45 | 43738.6562 | 43738.6979 | 1 | 1 | Logesh | 8348 | API -> CIA048 -> Notification System -> Opportunities - Not a Violation | Done | Task | 396fd58b-b4e9-e911-80fb-0cc47a092dc6
2019-10-01 15:47 | 43739.6576 | 43739.9076 | 6 | 6 | Logesh | 8349 | API -> CIA026 -> Report Manager -> View List | Done | Task | d45187cf-b4e9-e911-80fb-0cc47a092dc6
2019-10-01 15:47 | 43739.6576 | 43739.741 | 2 | 4 | Logesh | 8350 | API -> CIA027 -> Report Manager -> View Report details | Done | Task | 002076e0-b4e9-e911-80fb-0cc47a092dc6
2019-10-03 15:47 | 43741.6576 | 43741.741 | 2 | 4 | Logesh | 8350 | API -> CIA027 -> Report Manager -> View Report details | Done | Task | f5955fe9-b4e9-e911-80fb-0cc47a092dc6
2019-10-03 15:49 | 43741.659 | 43741.8257 | 4 | 4 | Logesh | 8351 | API -> CIA028 -> Report Manager -> Delete | Done | Task | 94149429-b5e9-e911-80fb-0cc47a092dc6
2019-10-04 15:51 | 43742.6604 | 43742.8271 | 4 | 4 | Logesh | 8352 | API -> CIA029 -> Report Manager -> Search | Done | Task | 1a197477-b5e9-e911-80fb-0cc47a092dc6
2019-10-04 15:53 | 43742.6618 | 43742.8285 | 4 | 4 | Logesh | 8353 | API -> CIA030 -> Report Manager -> Show home page setting | Done | Task | 51fca599-b5e9-e911-80fb-0cc47a092dc6
2019-10-08 14:15 | 43746.5938 | 43746.7604 | 4 | 4 | Logesh | 8361 | API -> CIA045 -> Notification System -> Reports - View violation comments | Done | Task | 4d9d67f6-a7e9-e911-80fb-0cc47a092dc6
2019-10-08 15:55 | 43746.6632 | 43746.8299 | 4 | 4 | Logesh | 8362 | API -> CIA046 -> Notification System -> Opportunities - View violation comments | Done | Task | 03aca3e7-b5e9-e911-80fb-0cc47a092dc6
2019-10-09 00:39 | 43747.0271 | 43747.1937 | 4 | 4 | Logesh | 8363 | API -> CIA049 -> Report Manager -> Whats Hot Video | Done | Task | 9c60015e-c8ea-e911-80fb-0cc47a092dc6
2019-10-10 | 43748 | 43748.125 | 3 | 4 | Logesh | 8363 | API -> CIA049 -> Report Manager -> Whats Hot Video | Done | Task | 9eb7794a-96f0-e911-80fb-0cc47a092dc6
2019-10-09 00:39 | 43747.0271 | 43747.1937 | 4 | 4 | Logesh | 8364 | API -> CIA050 -> Points Setup -> Active Package | Done | Task | 79fc3c54-c8ea-e911-80fb-0cc47a092dc6
2019-10-05 01:19 | 43743.0549 | 43743.0757 | 0.5 |  | Logesh | 8473 | CIA002: backoffice-> revoke admin access: user message is appear as wrong for revoke access | QA Verified | Bug | bff05519-e0e6-e911-80fb-0cc47a092dc6
2019-10-14 17:21 | 43752.7229 | 43752.8063 | 2 |  | Logesh | 8476 | CIA002: Backoffice-> revoke admin access: if user do revoke admin access and tries to logged in with the same user it should show proper alert but now it keeps logged in and showing following an error, refer screensshot | QA Verified | Bug | 549a4a01-79ee-e911-80fb-0cc47a092dc6
2019-10-05 01:19 | 43743.0549 | 43743.0757 | 0.5 |  | Logesh | 8478 | CIA008: Backoffice-> promote to admin->On activation, the message needs to appear as “USERNAME has been Promoted as admin user” in Snack bar. | QA Verified | Bug | db2ac301-e0e6-e911-80fb-0cc47a092dc6
2019-10-10 | 43748 | 43748.0833 | 2 |  | Logesh | 9194 | CIA016 - Report - Number of Violation Count is not displayed in Admin Panel | QA Verified | Bug | 998075d6-96f0-e911-80fb-0cc47a092dc6
2019-10-14 17:24 | 43752.725 | 43752.8083 | 2 |  | Logesh | 9201 | CIA044 - Block Account - When user click block user staus not changed but "Block successfully" message is displayed and unblock option not displayed | Removed | Bug | cd95ff59-79ee-e911-80fb-0cc47a092dc6
2019-10-14 17:22 | 43752.7236 | 43752.8069 | 2 |  | Logesh | 9202 | CIA044 - Block Account - Blocked user able to login into the application | QA Verified | Bug | bc7e3235-79ee-e911-80fb-0cc47a092dc6
2019-10-10 | 43748 | 43748.0417 | 1 |  | Logesh | 9203 | CIA012 > In Admin User grid, user should able to view selected user details by clicking on row in the grid. Currently, its not working. | QA Verified | Bug | 4948953a-96f0-e911-80fb-0cc47a092dc6
2019-10-11 17:29 | 43749.7285 | 43749.7701 | 1 |  | Logesh | 9203 | CIA012 > In Admin User grid, user should able to view selected user details by clicking on row in the grid. Currently, its not working. | QA Verified | Bug | 504ded13-7aee-e911-80fb-0cc47a092dc6
2019-10-10 | 43748 | 43748.0417 | 1 |  | Logesh | 9212 | CIA012> If the group owner deleted his group from the list, if any user mapped to that group means, in view of the selected user, deleted group should not be appeared. | QA Verified | Bug | 23854178-96f0-e911-80fb-0cc47a092dc6
2019-10-11 17:28 | 43749.7278 | 43749.7694 | 1 |  | Logesh | 9212 | CIA012> If the group owner deleted his group from the list, if any user mapped to that group means, in view of the selected user, deleted group should not be appeared. | QA Verified | Bug | 7e521df1-79ee-e911-80fb-0cc47a092dc6
2019-10-14 17:25 | 43752.7257 | 43752.809 | 2 |  | Logesh | 9251 | CIA018 - Notification System -> Reports - Delete - Notification not trigger to the user in the communication module | QA Verified | Bug | 0672318e-79ee-e911-80fb-0cc47a092dc6
2019-10-11 17:19 | 43749.7215 | 43749.8049 | 2 |  | Logesh | 9258 | CIA019 - Search - Search not working based on number of violations | QA Verified | Bug | 32e6fdb1-78ee-e911-80fb-0cc47a092dc6